## Project Planner
NSW Traffic Penalty Data Prog (Gantt Chart)
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Stage 1 (Planning) | 1 | 9 | 1 | 9 | 100% | bar: PERIODS 1 to PERIODS 9
1.1 Establishing team communication pathways | 1 | 2 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
1.2 Understanding / researching current systems | 1 | 2 | 1 | 1 | 100% | bar: PERIODS 1 to PERIODS 2
1.3 Producing a scope | 1 | 3 | 1 | 3 | 100% | bar: PERIODS 1 to PERIODS 3
1.4 WBS Structure | 1 | 4 | 1 | 7 | 100% | bar: PERIODS 1 to PERIODS 7
1.5 Development of Gantt Chart | 1 | 6 | 3 | 6 | 100% | bar: PERIODS 1 to PERIODS 8
Stage 2 (Design) | 10 | 10 |  |  | 0%
2.1 Create an idea / statement | 12 | 2 |  |  | 0%
2.2 Establish the project requirements | 13 | 2 |  |  | 0%
2.3 Establish software places in practice | 13 | 3 |  |  | 0%
2.4 Establish software places where not in practice | 13 | 3 |  |  | 0%
2.5 Establish system components | 15 | 3 |  |  | 0%
2.6 Template / Wireframe | 16 | 4 |  |  | 0%
Stage 3 (Software Development) | 20 | 11 |  |  | 0%
3.1 Allocation for software design leader (Unit Coding) | 20 | 10 |  |  | 0%
3.2 Implementing external software (PANDAS Software) | 20 | 10 |  |  | 0%
3.3 Input data from dataset | 22 | 4 |  |  | 0%
3.4 Construct data into readable form | 23 | 6 |  |  | 0%
3.5 Build GUI | 23 | 8 |  |  | 0%
Stage 4 (Implementation) | 31 | 6 |  |  | 0%
4.1 Training of end users | 31 | 3 |  |  | 0%
4.2 Updates / Status on system operations | 32 | 2 |  |  | 0%
4.3 Update any possible information / Bug fixing | 33 | 2 |  |  | 0%
4.4 User support and help documentation | 33 | 5 |  |  | 0%
Stage 5 (Closing) | 37 | 5 |  |  | 0%
5.1.1 Final Reporting | 37 | 5 |  |  | 0%
0%